# Operation Rainbow — Financial Proposal

Oct 6, 2026 · @Kusu

## Budget summary

The total project cost is ₦589,721,900. It covers building and deploying Operation Rainbow, plus 24 months of infrastructure and maintenance after go-live.

Operation Rainbow has three parts: a citizen and responder mobile app, an HQ command console, and a secure cloud backend. It also includes offline channels (USSD, SMS fallback and Bluetooth mesh) for when mobile data is down.

| Component | Period | Amount (₦) | Share |
| --- | --- | --- | --- |
| A. Build & deployment | Weeks 1–6 | 389,721,900 | 66.1% |
| B. Infrastructure & maintenance | 24 months after go-live | 200,000,000 | 33.9% |
| Total project cost |  | 589,721,900 | 100% |

## A. Build & deployment — ₦389,721,900

Software development is ₦295.8M (76%). Rollout across Plateau State is ₦82.7M, and the remaining ₦11.2M (2.9%) is held as contingency.

### A1. Software development

| # | Item | What it covers | Amount (₦) |
| --- | --- | --- | --- |
| 1 | Discovery, requirements & UX/UI design | Stakeholder workshops with HQ and agencies, workflows, screen designs for citizen, responder and HQ users | 18,500,000 |
| 2 | Mobile app (citizen & responder) | Android and iOS app: SOS with live location, incident reporting, duress PIN cancel, dispatch and missions, secure chat, live video | 72,000,000 |
| 3 | HQ command console | Live map, incident feed, dispatch, escalation up the command chain, agency portal, mass broadcast | 54,000,000 |
| 4 | Backend, database & data security | Database with row-level security, realtime updates, media storage, staff provisioning, duress-PIN logic | 38,500,000 |
| 5 | Offline channels | USSD menu, SMS fallback with encrypted payloads, Bluetooth mesh relay, HQ ingest endpoints | 42,000,000 |
| 6 | Live video & AI incident analysis | Responder video streaming to HQ and AI-assisted incident triage | 16,500,000 |
| 7 | Quality assurance & field testing | Automated tests, user acceptance testing, field tests across the 17 LGAs including no-data scenarios | 22,000,000 |
| 8 | Independent security audit | Penetration test and code review by a third party before go-live | 12,500,000 |
| 9 | Project management & documentation | Delivery management, reporting, operating runbooks and user manuals | 19,800,000 |
|  | Subtotal A1 |  | 295,800,000 |

### A2. Deployment & rollout

| # | Item | What it covers | Amount (₦) |
| --- | --- | --- | --- |
| 10 | Telecom provisioning | Dedicated USSD shortcode on MTN, Airtel, Glo and 9mobile; SMS shortcode and sender ID; aggregator onboarding | 14,500,000 |
| 11 | HQ command centre equipment | Operator workstations, display wall, UPS and power backup, network equipment | 32,000,000 |
| 12 | App store publishing, domains & licences | Google Play and Apple developer accounts, domain, SSL, initial licences | 1,200,000 |
| 13 | Training | HQ operators, responders and agency liaison officers | 13,500,000 |
| 14 | Public awareness & citizen onboarding | Radio jingles, flyers in English and Hausa, community sessions on how to raise an SOS and dial the USSD code | 15,000,000 |
| 15 | Go-live & hypercare | Production setup, cutover, and 4 weeks of on-site launch support | 6,500,000 |
|  | Subtotal A2 |  | 82,700,000 |

### A3. Contingency

| # | Item | What it covers | Amount (₦) |
| --- | --- | --- | --- |
| 16 | Build contingency (2.9%) | Exchange-rate movement on dollar-priced services and unforeseen scope | 11,221,900 |
|  | Total A (A1 + A2 + A3) |  | 389,721,900 |

## B. Infrastructure & maintenance (24 months) — ₦200,000,000

This averages ₦8,333,333 per month. Infrastructure is ₦96.8M, the support and maintenance team is ₦91.2M, and ₦12M (6%) is contingency.

### B1. Infrastructure

| # | Item | Basis | Amount (₦) |
| --- | --- | --- | --- |
| 17 | Production cloud backend | Database, realtime, compute, media storage, daily backups — ₦1,250,000/month | 30,000,000 |
| 18 | Staging environment | Separate test copy for safe releases — ₦150,000/month | 3,600,000 |
| 19 | HQ console hosting | Console hosting, notification worker, domain, SSL, CDN — ₦300,000/month | 7,200,000 |
| 20 | Live video relay servers | Relay (TURN) servers so responder video reaches HQ on poor networks — ₦400,000/month | 9,600,000 |
| 21 | SMS messaging | Sign-in codes, alerts and broadcasts, about 150,000 SMS/month — ₦750,000/month | 18,000,000 |
| 22 | USSD service | Shortcode renewal on 4 networks for 2 years, plus session charges | 14,000,000 |
| 23 | AI, maps, push & monitoring | AI triage API, map tiles, push notifications, uptime and error monitoring — ₦250,000/month | 6,000,000 |
| 24 | HQ internet connectivity | Primary and backup internet links — ₦350,000/month | 8,400,000 |
|  | Subtotal B1 |  | 96,800,000 |

### B2. Maintenance & support

| # | Item | Basis | Amount (₦) |
| --- | --- | --- | --- |
| 25 | Support & maintenance team | 24/7 on-call support, bug fixes, Android/iOS updates, security patches, minor enhancements — ₦3,000,000/month | 72,000,000 |
| 26 | Year-2 security audit | Annual penetration test and key rotation | 8,000,000 |
| 27 | Refresher training | Twice-yearly sessions for HQ operators and responders | 6,000,000 |
| 28 | HQ equipment maintenance & spares | Servicing and replacement parts for item 11 | 5,200,000 |
|  | Subtotal B2 |  | 91,200,000 |

### B3. Contingency

| # | Item | Basis | Amount (₦) |
| --- | --- | --- | --- |
| 29 | Operations contingency (6%) | Usage growth above forecast (SMS, storage) and exchange-rate movement | 12,000,000 |
|  | Total B (B1 + B2 + B3) |  | 200,000,000 |

## Payment schedule

The build takes 6 weeks and is paid in four milestones. Telecom networks can take several weeks to approve a USSD shortcode, so those applications are filed in week 1. Operations are then paid in 8 equal quarterly instalments of ₦25,000,000.

| # | Milestone | Deliverable that triggers payment | Timing | % of A | Amount (₦) |
| --- | --- | --- | --- | --- | --- |
| 1 | Mobilisation | Signed contract; project plan and team in place | Week 1 | 30% | 116,916,570 |
| 2 | Core system | Approved designs; working backend, mobile app and HQ console demonstrated | Week 2 | 25% | 97,430,475 |
| 3 | Acceptance | Offline channels working; user acceptance and field tests passed; security audit closed | Week 5 | 25% | 97,430,475 |
| 4 | Go-live | Apps live on Google Play and App Store; USSD live on all 4 networks; training done | Week 6 | 20% | 77,944,380 |
|  | Build subtotal |  |  | 100% | 389,721,900 |
| 5–12 | Operations (Q1–Q8) | Quarterly service report: uptime, incidents handled, fixes delivered | Quarterly in advance, from go-live |  | 8 × 25,000,000 = 200,000,000 |
|  | Project total |  |  |  | 589,721,900 |

## Assumptions and exclusions

Assumptions

- All amounts are in Nigerian Naira and are treated as inclusive of 7.5% VAT. If VAT must be added on top, the project total becomes ₦633,951,043.

- Cloud, SMS and API services billed in US dollars are budgeted at an assumed rate. Exchange-rate movement is covered by the contingency lines (items 16 and 29).

- SMS volume is planned at about 150,000 messages a month. Higher use is funded first from item 29.

- Build and deployment take 6 weeks from contract signing. The 24-month support period starts at go-live, at the end of week 6.

- The State provides the HQ premises, power supply and staff to be trained.

Not included

- Handsets or radios for responders and citizens.

- Civil works or furnishing at the HQ command centre.

- New features beyond the scope in A1, which are priced separately as change requests.

- Support after month 24, which can be renewed at the B rates.